## Sheet1
Biznify
| Frontend_website | https://biznify.getupdemo.xyz/ |  | dashboard | https://login.biznify.getupdemo.xyz/ | vercel | https://biznify.vercel.app/
Date | End/Platform | Page Name | Type | Section | Description | Attachment | Comment | Tester | Developer Approval | Asignee | ETC | Status | Assignee Comments | Notes
2023-08-31 | Frontend | homepage->FAQ |  | Frequently Asked Questions | single dropdown doesn't work, opens all other dropdowns in the section | att |  | Rubaba | Yes | Mamun bhai |  | Complete
| Frontend | homepage->Trusted by 100+ section |  | Trusted by 100+ Clients | all image icons must be same size | att |  | Rubaba | Yes | Mamun bhai |  | Complete
| Frontend | homepage |  | Hero area | unused space in left margin, cuts space for the image at the right margin. On 75% the design looks operational (pass), you may choose to ignore it if end user usage won't be hampered much. Image size = | att |  | Rubaba | Yes | Sagor |  |  | Design Issues
| Frontend | homepage |  | Biznify Serves A Wide Range of Industries and Businesses | item section and image section must be similar in size. fix ratio | att |  | Rubaba | No | Mamun bhai
| Frontend | homepage |  | Benefits of Using Biznify | item section and image section must be similar in size | att |  | Rubaba | No | Mamun bhai
| Frontend | homepage |  | Why Choose Biznify | item section and image section issue. Vercel and demo row columns need fixing, image should be outside content | att,att |  | Rubaba | No | Fahim bhai
| Frontend | homepage |  | A Comprehensive Business Management Solution for Every Product-Based Business | slider must work |  |  | Rubaba | No | Mamun bhai
| Frontend | homepage |  | Download our Mobile Apps for a better experience. / For a Better Experience, Download the Biznify Mobile App (vercel correspondance) | content and image may be of same ratio | att |  | Rubaba | No | Fahim bhai
| Frontend | homepage->footer |  | footer section | Trustpilot icon make it more visible | att,att |  | Rubaba | No | Fahim bhai
| Frontend | finance |  | header>apps>finance | Build completely | no attachment | Complete the page | Rubaba |  | Mamun bhai |  | In Progress
| Frontend | finance |  | Take Your business Growth Potential to the Next Level | image and content ratio must be fixed |  | section name has been modified and now i cannot find the section | Rubaba | No | Sagor |  | In Progress
| Frontend | Inventory and MRP |  | featured card section | image logo size needs to be fixed | cannot find section | fix the whole page | Rubaba |  | Sagor |  | In Progress
| Frontend | Inventory and MRP |  | Biznify streamlines and manages your inventory and production planning for optimal efficiency. | margin bottom is required after button and extra redundant space on the right. | att |  | Rubaba |  | Fahim bhai
| Frontend | Inventory and MRP |  | Dynamic Management | slider / image needs to be fixed | att,vercel |  | Rubaba |  | Sagor
| Frontend | Inventory and MRP |  | Streamline your entire business Inventory management system | should have slider for convenience | cannot find section, please any report modification | fix all section space and ratio | Rubaba |  | Fahim bhai
| Frontend | sales |  | whole page same as inventory and MRP | -- | no atatchment | similar issues regarding whole page development | Rubaba |  | Mamun bhai |  | Complete
| Frontend | marketing |  | -- | follow attachment and make changes. | att,att |  | Rubaba |  | Sagor
| Frontend | apps>dropdown |  |  | fix UI issue. check attachment | 1 |  | Rubaba |  | Sagor
| Frontend | refresh button |  | url | refresh brings 404 error. try refreshing no need for attachment | no attachment | going back does not work s well, same error | Rubaba |  | Mamun bhai |  | In Progress
| Frontend | addons |  | breadcrumbs | include proper title and subtitle IF NEEDED ONLY. |  |  | Rubaba | No | Mamun bhai |  | Hold
| Frontend | addons |  | addon main area | this section will have multiple addon cards , suggesting load more button | att | complete whole page | Rubaba |  | Mamun bhai |  | Complete
| Frontend | addons |  | addon nav bar | hover functionality must be made smooth, cursor works slow, search, categorizations (free/paid) does not filter the required services / products | 2 |  | Rubaba |  | Mamun bhai |  | Hold
| Frontend | addons |  | Integrate with MS Excel Addons>description | Related addons must have a working slider or load more button | att, vercel |  | Rubaba |  | Mamun bhai |  | Hold
| Frontend | addons |  | Integrate with MS Excel Addons> description | fix image content ratio os Need assistance? Reach out to an expert! see atatchment | 3 |  | Rubaba |  | Sagor
| Frontend | pricing |  | breadcrumbs | proper title and subtitle |  |  | Rubaba | No | Mamun bhai |  | Hold
| Frontend | pricing |  | tab area | must be maded dynamic, use slider |  |  | Rubaba | No | Mamun bhai |  | Hold
| Frontend | pricing |  | tab area | proper message, ex- basic 1000 tk for 2 people, with increase 500 tk will be added more with 1000. see attachment | 4 |  | Rubaba |  | Mamun bhai |  | Complete
| Frontend | e-store templates |  | template filter area | hover is bad, cursor slow, dropdown ocassionally works |  | incomplete | Rubaba |  | Fahim bhai |  | Complete
| Frontend | resources |  | contact us > Let's have a talk | Design problems, overlapping, input value validation required. See attachment | 5 |  | Rubaba |  | Sagor
| Frontend | resources |  | products | bradcrumbs need proper title and subtitle IF NEEDED. |  |  | Rubaba | No | Mamun bhai |  | Hold
| Frontend | resources |  | products>Attendance devices,POS devices, Tablet devices | load more button is required for multiple . SUGGESTION | att |  | Rubaba |  | Sagor
| Frontend | resources |  | mobile apps breadcrumbs area | image fitting needs to be propwe see attachment | 6 |  | Rubaba |  | Sagor
| Frontend | resources |  | mobile apps feature area | check if the content , image ratio is proper | 7 |  | Rubaba |  | Sagor
| Frontend | resources |  | changelog | complete page | att |  | Rubaba |  | Mamun bhai |  | Complete
| Frontend | billing info (icon) |  | home>checkout>billing info | fix design problems, overlapping problems, check box icon not clearly visible etc |  |  | Rubaba |  | Sagor
| Frontend | sign in |  | reset password | must appear the correct prompts, must accept and validate all input types, see attachment | 8 |  | Rubaba |  | Mamun bhai
| Frontend | header |  | biznify icon | subtitle not clear for all device type like laptops, tablets, fix ratio and size, see attachment | 9 |  | Rubaba |  | Sagor
| Dashboard | dashboard categories |  | categories | with every click on the categories, it goes up again. check attachment and ask me if you don't understand | 10 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | pages |  | dashboard>pages, seo, all messages, | UI fixing necessary. See attachment | 11 |  | Rubaba |  | Mamun bhai |  | Complete
03.09.23 | Dashboard | dasboard | Bug | static slider | Image fitting needs fixing. Examples - vercel image is 793x760 while in demo when new image is uploaded size is 624x500. how is it still larger than the vercel. Check attachments | 12,13 |  | Rubaba |  | Sagor |  | Complete
| Dashboard | dashboard categories | Modification | core values | suggested to have a load more button and "description" field should be restricted and reevaluated as it also takes complete special character values like " ------- " | 14 |  | Rubaba |  | Mamun bhai |  | Hold
| Dashboard | dashboard categories | Bug | Intergrate | Spelling error shoule be INTEGRATE not INTERGRATE. Also serach button not working, also enable partial search. see attchment | 15 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard categories | Modification | dashboard>Intergrate | Suggested to have a load more button for volumetric input. Also it takes single special character as description. restrict and validate |  |  | Rubaba |  | Mamun bhai |  | Hold
| Dashboard | dashboard categories | Bug | dashboard>Our work | fix image sizing, see attachment. Background image 1170 x 638 | 16 |  | Rubaba |  | Sagor |  | Complete
| Dashboard | dashboard categories | suggestion | dashboard>Our work | suggestion for buton links never to accept anything without a valid link. Just a suggestion |  |  | Rubaba |  | Mamun bhai |  | Hold
| Dashboard | dashboard categories | Bug | testimonials | UI issue, invalid input in name, description, designation. See attachments | 17 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard categories | Bug | testimonials | testimonial title image is not showing on frontend . See attachment | 18,19 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard categories | Bug | dashboard>features | dashboard UI issues. Check attachment please | 20 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard categories | Bug | dashboard>features | fix image size issue.Also fix space ratio of website content See attachment | 21,22 |  | Rubaba |  | Sagor |  | In Progress
| Dashboard | dashboard categories | Bug | dashboard>features | limit given 200 characters in description box but takes more. See attachment | 22,23 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard categories | Bug | dashboard>Applications | fix a character limit for "description" there is none as of yet. |  |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard categories | Modification | dashboard>Applications | fix image size limit. For portrait and landscape dimensions. See attachments | 24,25 |  | Rubaba |  | Sagor |  | Complete
| Dashboard | dashboard | Bug | dashboard>happy clients | Limit upto 20 character intake. See attachment | 26 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | dashboard>Industry CRM | title media invisible in website. Where is it? | 27 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Modification | dashboard>Industry CRM | limit title limit to 20 characters. See attachment | 28 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | suggestion | dashboard>Industry CRM | limit description of this section to 300 characters | 29 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | dashboard>FAQ | limit exceeded 200 characters which was defined. And image is being veiled or hidden in wedbsite See attachment | 30,31 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | dashboard>FAQ | limit question title length | 31 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | mobile apps>title | restrict invalid rating input 9/5 and fix the title image positioning. See attachment | 32 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | mobile apps>title>image | fix image dimension else designs breaks / misplaced | 33,34 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | dashboard | Bug | mobile apps>feature | fix feature image position with proper padding and margin, size, title, subtitle, description character limit. See attachment | 35 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | dashboard | Modification | mobile apps>feature> Add new | fix title and description character limit, as well as dashboard UI. SEE ATATCHMENT! | 36 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Modification | mobile apps>widgets | fix title and description character limit, image content ratio on website. SEE ATATCHMENT! | 37 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | dashboard | Bug | mobile apps>widgets | title can't be inserted . see attachment | 38 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Modification | mobile apps>widgets | changing widget thumbnail shifts the zigzag structure to normal structure of the images see attachment | 39,40 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | dashboard | Bug | mobile apps>widgets | description box has limit of 200 characters but input exceeds the limit. Fix it |  |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | suggestion | mobile apps>Showcases | might want to reduce the title character limit a bit, even though it is restricted |  |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Modification | mobile apps>Showcases | image size has to be mentioned else the design breaks. see attachments | 41 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | dashboard | Bug | mobile apps> FAQ | FAQ s' are different in dashboard for each section however appears same on website also any updates and additions of FAQ is not shown in websiite. see attachment | 42 |  | Rubaba |  | Sagor |  | In Progress
| Dashboard | dashboard | Modification | Changelog | on website, the newly added logs are adding up from bottom keeping a space on top. see attachment | 43 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | dashboard | Bug | changelog>topics | exceedes given character limit of 200. See attachment | 44 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | addons | update button not working, update not happening on dashboard. | 45 |  | Rubaba |  | Mamun bhai |  | Complete
| Dashboard | dashboard | Bug | addons> add new | cannot be added in dashboard, save button not working, fix input validation criteria check attachment for details | 46 |  | Rubaba |  | Mamun bhai |  | Complete
| Frontend | website | Modification | addons | fix UI issue. See attachment | 47 |  | Rubaba |  | Sagor |  | Hold
| Dashboard | Dashboard Packages | Bug | Dashboard> Packages> Package categories | Add New button doesnot work. | V1 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard Packages | Bug | Dashboard> Packages> Package categories | Decativation package doesnot work. | V2 |  | Vasha |  | Mamun bhai |  | Hold
| Dashboard | Dashboard Packages | Bug | Dashboard> Packages> Packages | Add New button doesnot work. | V3 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard Packages | suggestion | Dashboard> Packages> Packages | There must be a selection option of Package Category Types |  |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard Packages | Bug | Dashboard> Packages> Features | Package feature order does not show same in dashboard and website | V4 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Header | Header Menu does not decatived | V5 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Header | Header Menu name does not change. | V6 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Header | Add New Menu Option must be requied. |  |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Footer | Cannot add or delete any footer links or pages. |  |  | Vasha |  | Mamun bhai |  | Hold
| Dashboard | Dashboard | Bug | Footer> App Feature Link | Feature five name does not change, It represents as same as URL on the dashboard | V7 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Footer> Quick Links | Quick Link( five )name does not change, It represents as same as URL on the dashboard | V8 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Footer> Pages | Page-4 doess not show the footer of website | V9 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Footer> Pages | Slug of Page-2 does not change | VV |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard | Bug | Footer> Footer Logo | Logo image does not change | V10 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard Setting | Bug | Setting> General Info | Favicon does not change in website | V11 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard Setting | Bug | Setting> Pages | Pages are not active |  |  | Vasha |  | Sagor |  | Hold
| Frontend | Contact Us | Bug | Email issue | Email address can be more than 20characters. | V13 |  | Vasha | Yes | Mamun bhai |  | Complete
| Dashboard | Dashboard> Messeages | Bug | Messeages> All Messages | Take invalid input for user name in message. | v14 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard> Apps | Bug | Apps> Features> Faq | Cannot change faq image. | V15 |  | Vasha |  | Mamun bhai |  | Hold
| Dashboard | Dashboard> Apps | Bug | Apps>Modules>Manage Modules> Add new> CTA | CTA image is not showing in website. | V16 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard> Subscription | Bug | Subscription | Subscription does not work | V17 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard> Apps | suggestion | Apps> Modules> Widgets> Description | Description field should not be more than 200 charaters | v18 |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | Dashboard> Apps | suggestion | Apps> Modules> Departments> Description | Description field should not be more than 200 charaters |  |  | Vasha |  | Mamun bhai |  | Complete
| Dashboard | [6 empty] | Vasha
| Dashboard | [6 empty] | Vasha
| Dashboard | [6 empty] | Vasha
| Dashboard | [6 empty] | Vasha
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard