## Issues
| Loader Commission Issues |  |  | Total=17 | On Queue=6 | Correction=0
|  |  |  | In Progress=0 | In Review=0 | Done=11
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
1 | Correction | Counter | The particular for Loader Commission expense should be same as other expenses particular . "BUEA - YAOUNDE_13-02-2024 23:00 BUA - YDE N 004" | Normal | Done | https://prnt.sc/uXRuE5KntbU-
2 | Correction | Counter | Expense isn't showing here | Normal | Done | https://prnt.sc/SclC8h4Vf_VA
3 | Correction | Counter | Why it's different? is the today income counter wise? then make it user wise. This dashboard will be user wise | Normal | Done | https://prnt.sc/7sUikDlhiksJ
4 | Correction | Counter | This two field need to block by disable color | Normal | Done | https://prnt.sc/p_NjXgO70Mbg
5 | Correction | Counter | After submit it send the request but no messge is showing here. | Normal | Done | https://prnt.sc/1XyPhxHn597i
6 | Correction | Counter | Afer canceling a ticket, the loader commission isn't deducting. Before cancel it was 3 seats. the commission was 750. After cancel a seat it should be 500 | Normal | Done | https://prnt.sc/hN9z9UGDaGKr https://prnt.sc/PywnLM43197N
7 | Correction | Admin | No Loader Commission expense showing in this report | Normal | Done | https://prnt.sc/nIPJl-wtr8Ra
8 | Correction | Admin | No Loader Commission expense showing in this report. | Normal | Done | https://prnt.sc/J7aqvsRVSvcj
9 | Correction | Admin | Apply loader commission checkbox in "Fleet Type" Edit section from Admin for managing loader commission | Normal | Done | https://prnt.sc/2CTSDVIBJhGR
10 | Correction | Admin | No Loader Commission expense showing in this report. | Normal | Done | https://prnt.sc/WLeMrjFHwiRC
11 | Correction | Agent app | The loader commission isn't showing in agent app | Normal | Done | https://prnt.sc/xDHJIBYByn9V
12 | Correction | Agent app | Make sure my statement of app the loader commission isn't showing as like coutner statement | Normal | On queue
13 | Correction | Admin | I've removed the loader commission accounts head. So, for the expense report. Make sure the loader commission will show in the filter as well | Normal | On queue
14 | Correction | All | Need to check cancel of other user ticket. | Normal | On queue
15
16
17
18 |  |  | New Issues - Musango Beta
1 | Correction | Counter | Loder Commission result not found in "Head Search" | Normal | On queue | https://prnt.sc/6SsTGBoqqHfe
2 | Correction | Counter | Balance Head Not found | Normal | On queue | https://prnt.sc/fq88hNKTRtCh
3 | Correction | Admin | Add comma in sales amount from admin panel > " sales report '' | Normal | On queue | https://prnt.sc/d0t1ywpti3vE

## Update Issues
| Loader Commission Issues |  |  | Total=0 | On Queue=0 | Correction=0
|  |  |  | In Progress=0 | In Review=0 | Done=0
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
Single Ticket book - Checked (loader comission not added)
Single Ticket sell - Checked (loader comission added)
Single Ticket sell with discount - Checked (loader comission added except discount amount)
Multiple Ticket sell- Checked (loader comission added except discount amount).
Multiple Ticket sell with discount - Checked (loader comission added except discount amount)

## Tables
Type | Priority | Status | Platform
Typo | Normal | On queue | Admin
Correction | Medium | In progress | Counter
Content | High | In review | Agent app
Feature |  | In revision | Android app
Bug |  | Done | iOS app
Broken Link |  |  | Website
New Task |  |  | Parcel
Improvement |  |  | Driver App
All