## Rakaab Beta
| Bus Project Issues |  |  | Total=21 | On Queue=6 | Correction=4
|  |  |  | In Progress=0 | In Review=0 | Done=11
SL | Type | Platform | Tasks | Priority | Status | Screenshots | Note
1 |  |  | Rakaab Beta (Client Issues)
2 | Correction | Counter | After Admin changes the Exchange rate then, if the counter user does not refresh the price will continue as it is. | Normal | Done | https://prnt.sc/4bjfc4XwzmMH | If the Admin changes the Exchange rate then if the counter user does not refresh the price will continue as its. Ans: If the counter doesn't refresh the ticket won't be sold it will show an error message.
3 | Correction | Counter | Departure Sheet, ticket price is incorrect. | Normal | Done | https://prnt.sc/5IJLPly4TfmH
4 | Correction | Counter | After change currency from counter header bar, departure Sheet ticket price is incorrect. | Normal | Done | https://prnt.sc/adK4xrQDJJ7D
5 | Correction | Admin | After canceling any seat, from the admin the cancellation amount is different from the original ticket price. it's greater than the original ticket price actually | Normal | Done | https://prnt.sc/xgCPM6feMn2i | Once I cancel any seat, the cancellation amount that will appear on the ticket cancel request page from the admin is different from the original ticket price. it's greater than the original ticket price actually
6 | Correction | Admin | Parcel and ticket sales report is not accurate. This means value is not accurate | Normal | In revision
7 | Correction | Admin | Commission module report: once I select Shilling currency then I will found 0 | Normal | In revision | https://prnt.sc/dm6WNeGQRuKJ
8 | Correction | Admin | I cannot check the Route wise report for the parcel because it's just loading. I couldn't get a result or any value. | Normal | In revision
9 | Correction | Admin | Route-wise summary: once I select the Shilin type, Amount of tickets column, Balance column and Net Column which is last column is empty so I can't check its value | Normal | In revision | https://prnt.sc/KFamU8gVHbD5
10 | Correction | Admin | The Sales Report is missing the ticket price once selected Shilling Currency type | Normal | Done | https://prnt.sc/fwewNY9y4VJD
11
12 |  |  | New Issues - Rakaab Beta
13 | Bug | Counter | After click on book ticket price not show. | Normal | On queue | https://prnt.sc/dlp9GdA0o7Tq
14 | Correction | Counter | After change currency from counter header bar, then search with PNR. The currency not changing from Fare | Normal | Done | https://prnt.sc/TNcPpqlkRs_9
15 | Bug | Counter | Cancel Ticket Not showing in User Dashboard | Normal | Done | https://prnt.sc/UqzHsJbNqjbN
16 | Bug | Counter | Cancel Ticket Not showing in "My statement" | Normal | Done | https://prnt.sc/w1g8CzvXt2Ln
17 | Bug | Admin | Ticket sales report is not accurate (value is not showing accurately) | Normal | Done | https://prnt.sc/ut-QyaNWtVoi https://prnt.sc/9iOrNrW41BFQ
18 | Bug | Admin | Commission Model Report value is not showing accurately | Normal | On queue | https://prnt.sc/qv0E6caQB-Nh https://prnt.sc/rzeVLGOPmTSM | Didn't add any commission model for this sale, bt still it's showing
19 | Correction | Counter | In "My sales report " only cancel ticket data is not showing. It's just loading. | Normal | Done | https://prnt.sc/IXfzgmNpKRA4
20 | Correction | Counter | After changing curruncy from the counter header, the Dashboard tickets data not changing. | Normal | Done | https://prnt.sc/0SkTSWEdIIhZ
21 | Correction | Admin | The section should be correction | Normal | On queue | https://prnt.sc/3VGVR3cv8zgY
22 | Correction | Admin | In "My Sale" report only "Without Cancel" ticket data is not showing. It's just loading. This issue sometimes happen for some user, not all users. | Normal | On queue | https://prnt.sc/WqPonkWfUW33
23 | Feature | Counter | In passenger details select Genter functionality not working smoothly, need to click atleast 3/4 times to select Gender type in "Female" | Normal | On queue | https://prnt.sc/yF6eHeXidvMd
24 | Correction | Counter | After change currency in (Birr) from counter header bar, my statement currency should be selecte at this by deafult currency (Birr) | Normal | On queue | https://prnt.sc/Hf9dLP7Y_3iV

## Tables
Type | Priority | Status | Platform
Typo | Normal | On queue | Admin
Correction | Medium | In progress | Counter
Content | High | In review | Agent app
Feature |  | In revision | Android app
Bug |  | Done | iOS app
Broken Link |  |  | Website
New Task |  |  | Parcel
Improvement |  |  | Driver App
All