## XPeed (Demo)
Site Link`1 | XPeed (Demo) | Login URL | https://xpeed.getupdemo.xyz/login | Email/Username |  | Password |  | 2HO%)2isX1~}~x(
Type | Feature | Description | Priority | Developer Approval | Attachment | Assignee | ETC | Status | Assignee Comments | Notes
Modification | Backend Header | Header menu's should be editable, so that menu can be customized as we want. | Normal | YES | https://prnt.sc/GOpYw6z4zUJ6 | Mamun |  | Complete
Bug | Header Setting | Need to fixed Logo size. | Normal | YES | https://prnt.sc/iEfWxBBoTkkf | Sagor |  | Complete
Modification | Backend Features | Features icon need to customized, so that user can upload any images form their device. | Normal | YES | https://prnt.sc/waY59aetRSSV | Mamun |  | Complete | size and color need to be fixed by Sagar
Bug | Hero Sliders | Need to Increased the slider changes speed | Normal | YES | https://prnt.sc/-Ns7jG-A0r79 | Sagor |  | Complete
Bug | Clients | Clients logo size need to fixed...it showing half logo on the font site... | Normal | YES | https://prnt.sc/gr1GBf3tl5o9 | Sagor |  | Complete
Bug | What we do | Not showing list icon | Normal | YES | https://prnt.sc/8fnaQltMx9nl | Sagor |  | Complete
Bug | Pricing | Not support more then 20 characters in pricing button text | Normal | YES | https://prnt.sc/gWf5tYutrq3F | Mamun |  | Complete
Bug | Pricing Category | Category position isn't changing | Normal | YES | https://prnt.sc/dvGHpfVxsn-6 | Mamun |  | Complete
Modification | All Package Request | Package Order Request from need to modify like that attached image. | Normal | YES | https://prnt.sc/seCAcOi12r4F | Mamun |  | Complete
Modification | All Messages | A feature is required to delete all or specific messge requests with download data as a CSV file. | Normal | YES | https://prnt.sc/V9R7r6-8OC0B | Mamun |  | Complete | data download feature is incomplete
Modification | What we do | Need a delete option to remove or delete services (card one, card two). Also add Insert card. | Normal | YES | https://prnt.sc/50DiIc_uynCN | Mamun |  | Complete
Bug | Explore | It doesn't work when I put the internal link in card-two. | Normal | YES | https://prnt.sc/6RNsdv9hxYyp | Mamun |  | Complete
Modification | Products | Not able to delete all products, this needs to be modified so that user can delete all products if they don't have any products to sell. | Normal | YES | https://prnt.sc/o1l4HdlTvILi | Mamun |  | Complete
Modification | FAQ | Need to decrease the gap between the Faq title and the question on the front site. | Normal | YES | https://prnt.sc/_iHdgKPR7jaR | Sagor |  | Complete
Bug | Testimonial | Not able to delete all testimonials. | Normal | YES | https://prnt.sc/kV6S6-YBQDZm | Mamun |  | Complete
Bug | Testimonial | Not showing five star | Normal | YES | https://prnt.sc/DhXcdc8BXpJz | Mamun |  | Complete
Modification | Footer Setting | Need to add a new Phone Number input box | Normal | YES | https://prnt.sc/QlJNJhkRRnnx | Mamun |  | Complete
Modification | Footer Setting | Need to a email icon in footer section | Normal | YES | https://prnt.sc/iIqjSO37c3-Z | Mamun |  | Complete | user can upload svg or png icon.
Modification | Footer Setting | Need to add a features for add or delete social media links | Normal | YES | https://prnt.sc/fJYGbEEI3nsY | Mamun |  | Complete
Bug | Pages | Need to fix all pages url for internal linking | Normal | YES | https://prnt.sc/DV7qx-YYPLVF | Mamun |  | Complete | The user can add a custom URL if they want.
Bug | Contacts | Need to fix image size | Normal | YES | https://prnt.sc/nayq7WwFsqmx | Sagor |  | Complete
Modification | Speed Test | Don't have any section to edit speed test page in the backend | Normal | YES | https://prnt.sc/uwTDnSADOvoJ | Mamun |  | Complete
Bug | Products | Don't have any field to edit discount amount of product section in the backend | Normal | YES | https://prnt.sc/7uPE8qewoYJ4 | Mamun |  | Complete
Modification | Contacts | contact us page needs to modify like the attached image. and also a fill required for add links to chat box | Normal | YES | https://prnt.sc/WUMW9FOpQSWu | Mamun |  | Complete | image size need to be fixed by Sagar
Investigation | Paybill | 1 paybill tab should be like this | Normal | YES | https://prnt.sc/XnL3a4kJpAr8 | Mamun |  | Complete
Investigation | Backend Features | A feature is required to add or remove user also change user email and password | Normal | LATER |  | Mamun |  | Hold | Need to discuss in person
Investigation | Backend Features | Dashboard favicon not working | Normal | YES |  | Mamun |  | Complete | worked on almost all view pages might miss one or two pages mistakenly. need to test every page very carefully and report to me if any error found.
Modification | All Package Request | There are some modifications needed in the all package request end. A request status (like solved, unsolved, contacted etc) should be added. Also there should have a request archieve option where solved requests should be archieved. Lastly, new request should be in the top of the list where it comes at the bottom of the list now. | Normal | YES | https://prnt.sc/cbFlSwnH0ndm | Mamun |  | Complete
Modification | All Messages | There are some modifications needed in the all messages end. The page should be dynamic rather than static. A status (like solved, unsolved, contacted etc) should be added. Also there should have a request archieve option where solved requests should be archieved. Lastly, new request should be in the top of the list where it comes at the bottom of the list now. | Normal | YES | https://prnt.sc/2V7kKmQ2DI4y | Mamun |  | Complete
Modification | All product request | There are some modifications needed in the all product request end. The page should be dynamic rather than static. A request status (like solved, unsolved, contacted etc) should be added. Also there should have a request archieve option where solved requests should be archieved. Lastly, new request should be in the top of the list where it comes at the bottom of the list now. | Normal | YES | https://prnt.sc/9613eX0MQQty | Mamun |  | Complete
Modification | All Package Request | Action Button | Normal | YES |  | Mamun |  | Complete
Modification | All product request | Action Button | Normal | YES |  | Mamun |  | Complete
Modification | Topbar | Anchor tag hover color need to be changed when topbar background color is black. | Normal | YES |  | Sagor |  | Complete | Front end issue
Modification | Pages | All page Save Header Button should be only Save text | Normal | YES |  | Mamun |  | Complete
Investigation | Hero Sliders | a fill required to add background image for each slider | Normal | YES | https://prnt.sc/JJgT7m2QPjy- | Mamun |  | Complete | Front End slider need to be fixed by Sagar
Modification | Paybill | Bank Transfer Payment is not actually mandatory. There must be a section to pay bill online from any third party payment gateway like "SSLCommerZ". The main thing is; there should be a rectangular banner. Below that there must be checkbox with button. without checking that box, button won't work. See Reference. | Urgent | YES | https://prnt.sc/P_TRPrHVDKSz https://exordonline.com/pay-bill/ | Mamun |  | In Progress
Bug | Pages | Page slug must be dynamic. User Can modify that whatever they want. | Urgent | YES | https://prnt.sc/fpY7cyULebxt | Mamun |  | Complete
Modification | Pages | Dynamic Loader | High | YES |  | Mamun |  | In Progress
Modification | Pages | Offer Modal | High | YES |  | Mamun |  | In Progress
Modification | Pricing | Serial Maintain | High | YES |  | Mamun |  | Complete
Modification | All Package Request | there should be a confirmation popupn massages after sucessfull order placement or product purchase also contact us page | High | YES |  | Mamun
Modification |  | https://pollinetbd.com/ https://diginet.com.bd/ https://speedtechonline.com.bd/ http://bornointernet.com/ http://prefixnet.net/ https://deshnetbd.com/ https://greennetbd.com/ | Urgent | YES |  | Mamun
|  | Preloader should be removed....command by murad vai | Urgent | YES |  | Mamun | 2023-06-15 | In Progress
Bug | Pricing | Drag and Drop | Urgent | YES |  | Sagor |  | In Progress
Modification | Pages | Offer Modal | Urgent | YES |  | Sagor |  | Complete
Modification |  | Hero slider class problem | Urgent | YES |  | Sagor
Modification |  | Offer Modal Design | Urgent | YES |  | Sagor
Modification | Header Setting | Need a feature to delete existing menu and also need a feature to change Menu position. | Urgent | YES | https://prnt.sc/TIZyg4iKeDpn | Mamun
Modification | Features | need a feature to change features content | Normal | YES | https://prnt.sc/aNkA6MjdWohv | Mamun
Modification | Questions | contact us button link isn't working |  | YES | https://prnt.sc/kFK5okoAltRD
Modification | About us | can't able to edit About Us page title description.. | High | YES | https://prnt.sc/S9vAWJ2DzAzn | Mamun
Bug | Media | Error in Media Server Page | Urgent | YES | count(): Argument #1 ($value) must be of type Countable¦array, null given (pollinetbd.com) | Mamun
Bug | Backend Features | Fix the issue (Dashboard Logo & Admin Name changes) | Urgent | YES | https://prnt.sc/55iJoDQC19yg | Mamun
| Paybill | Paybill button link need to be dynamic | Urgent | YES
| Paybill | Bank button need to be dynamic |  |  | https://prnt.sc/pevNBcJrdlvs | Mamun
| Footer Setting | need to fix footer section font and address icon |  |  | https://prnt.sc/Jm8YM3uRgtfu | Sagor
[5 empty] | https://prnt.sc/8KMF8-VaUS3F | Mamun
DIGINET
Bug | Header Setting | The "Login" button needs to be dynamic. | Urgent |  | https://prnt.sc/lTTyBRLegGEk | Mamun |  | Complete |  | Requirement is not valid
Bug | Pricing Category | Require a rearrange feature to arrange pricing categories. | Urgent |  | https://prnt.sc/GnURsTLLB1HA | Mamun |  | Complete
Bug | Paybill | Can't input more than 10 characters in the bank account number, this limit must be at least 15 characters. | Urgent |  | https://prnt.sc/TeZtCKP9b9T8 | Mamun |  | Complete
|  | Diginet's website takes too much time to load, need to optimize its performance to reduce the loading time or speed.0 | Urgent |  |  | Fahim |  | Complete
Bug | Paybill | In the paybill section, steps image for bkash, nagad payments is not displaying on the mobile version. | Urgent |  | https://prnt.sc/lsodrLvmJBU- | Sagor |  | Complete
Bug | Contacts | third fill data of the 'Chat With Us' box is not changing. | Urgent |  | https://prnt.sc/l4mGE1ybUCZ9 | Mamun |  | Complete
Bug | Header Setting | Top header is not displaying on the mobile version. | Urgent |  | https://prnt.sc/e0Q0yA6Yhkas | Sagor

## Xtreme (Demo)
| X-Treme (Demo) | Login URL | X-Treme (Login) | Email/Username | demo@getup.com.bd | Password | 9$@3M1r#9GqE
Bug ID (autogenerate) | Type | Feature | Description | Priority | Attachment | Assignee | Status | Assignee Comments | Notes
BUG - 0001 | Modification | Header Setting | Logo height should be in 'auto' |  | https://prnt.sc/KhcaCjeoX7Vn | Fahim | Complete
BUG - 0002 | Bug | Hero Sliders | There is no welcome note. It should have been added |  | https://prnt.sc/z7oW8FENrkK7 | Fahim | Complete
BUG - 0003 | Bug | Backend Header | logo in svg format results in error |  | https://prnt.sc/zZV8oCNgaASD | Fahim | Complete
BUG - 0004 | Bug | Hero Sliders | Extra 'us' should be removed |  | https://prnt.sc/HqaFuXEUy7J4 | Fahim | Complete
BUG - 0005 | Modification | Hero Sliders | Illustration on the slider should be dynamic. |  | https://prnt.sc/I-gnoU2iHcoj | Fahim | Complete
BUG - 0006 | Bug | Hero Sliders | Word limit in the Hero content title should be exceeded |  | https://prnt.sc/u9VnP9CeAXP5 | Sagor
BUG - 0007 | Bug | Backend Header | Logo in png format results in error too |  | https://prnt.sc/HP6apM5SYw2o | Fahim | Complete
BUG - 0008 | Bug | Services Backend | Replaced icon could not preview. It shows only the previous one even when a new icon added |  | https://prnt.sc/GsjytBLpLkKb | Fahim | Complete
BUG - 0009 | Bug | Pricing Category | Descriptions of the pricing categories did not change even it has been edited at the backend. Also, it is found to be edited sometimes and somestimes didn't. need a proper solution. |  | https://prnt.sc/vBx98yJJK5Zz | Fahim | Complete
BUG - 0010 | Modification | Pricing Category | Most Popular badge should be added on the pricing category | Normal | https://prnt.sc/Onza0eyP1d0i | Fahim | Hold
BUG - 0011 | Modification | Products | a Load More button should be added at the end of the products category | Normal | https://prnt.sc/Agguutgo4f-z | Fahim | Hold
BUG - 0012 | Modification | Media Category | a Load More button should be added at the end of the media category | Normal | https://prnt.sc/enxaVt2ocOte | Fahim | Hold
BUG - 0013 | Bug | Titles | All the titles text should be editable like giving underline and changing the font sizes etc |  | https://prnt.sc/J_OOj9pOP7G4 | Mamun | Hold
BUG - 0014 | Modification | Google map | Google map should be colorful |  | https://prnt.sc/K4mWIU9Nx2ci | Fahim | Complete
BUG - 0015 | Bug | Pages | all the pages found invalid |  | https://prnt.sc/sYnwYUW0cm52 | Fahim | Complete
BUG - 0016 | Bug | Footer Setting | Nothig can be edited in the footer section. It shows error |  | https://prnt.sc/BQlLH3zXgbwt | Fahim | Complete
BUG - 0017 | Bug | Paybill | Add new bank results in error |  | https://prnt.sc/eLteIzSofNz- | Fahim | Complete
BUG - 0019 | Modification | Footer Setting | More payment logo should be added from the backend and also verified by option is missing |  | https://prnt.sc/gMbracjcPPfQ | Fahim | Complete |  | Merge the icons and upload as a single image
BUG - 0020 | Bug | Blog | Thumbnail should be previewed specifically |  | https://prnt.sc/z6YznmtgIvOH | Fahim | Complete
BUG - 0021 | Bug | Media Category | media server input at backend results invalid |  | https://prnt.sc/cCmeyxiJsNIs | Fahim | Complete
BUG - 0022 |  |  |  |  | https://prnt.sc/ZtK2D3q5oAWE | Mamun | Complete
BUG - 0023 | Modification |  | Change the all save button text. Add only (Save) text. |  |  | Mamun | In Progress
BUG - 0024 | Modification | All Package Request | There are some modifications needed in the all package request end. The page should be dynamic rather than static. A request status (like solved, unsolved, contacted etc) should be added. Also there should have a request archieve option where solved requests should be archieved. Lastly, new request should be in the top of the list where it comes at the bottom of the list now. |  | https://prnt.sc/cbFlSwnH0ndm | Mamun
BUG - 0025 | Modification | All Messages | There are some modifications needed in the all messages end. The page should be dynamic rather than static. A status (like solved, unsolved, contacted etc) should be added. Also there should have a request archieve option where solved requests should be archieved. Lastly, new request should be in the top of the list where it comes at the bottom of the list now. |  | https://prnt.sc/2V7kKmQ2DI4y | Mamun
BUG - 0026 | Modification | All product request | There are some modifications needed in the all product request end. The page should be dynamic rather than static. A request status (like solved, unsolved, contacted etc) should be added. Also there should have a request archieve option where solved requests should be archieved.Lastly, new request should be in the top of the list where it comes at the bottom of the list now. |  | https://prnt.sc/9613eX0MQQty | Mamun
BUG - 0027 | Bug | Testimonial | All the dummy testimonials could not be removed |  | https://prnt.sc/GNXks3FjDIBC | Mamun
BUG - 0028
BUG - 0029
BUG - 0030 | Modification | Paybill | Bank Transfer Payment is not actually mandatory. There must be a section to pay bill online from any third party payment gateway like "SSLCommerZ". The main thing is; there should be a rectangular banner. Below that there must be checkbox with button. without checking that box, button won't work. See Reference. | Urgent | https://prnt.sc/P_TRPrHVDKSz https://exordonline.com/pay-bill/ | Mamun | Complete
BUG - 0031 | Bug | Pages | Page slug must be dynamic. User Can modify that whatever they want. | Urgent | https://prnt.sc/fpY7cyULebxt | Mamun | Complete
BUG - 0032 | Modification | Pages | There should have been list shorting option in the backend for (Services, Funfacts, FAQ, Pricing Category, Pricing list, Package request, Paybill list, Bank list, Blog Category list, Blog list, All media category, all media and all products list) | Urgent |  | Mamun | Complete
BUG - 0033 | Modification | Hero Sliders | Slider features in the back end should be as similar as Xpeed. |  |  | Mamun | Complete
Complete

## Basic (Bugs)
Site Link | X-Treme (Demo) | Login URL | X-Treme (Login) | Email/Username | demo@getup.com.bd | Password | 9$@3M1r#9GqE
Bug ID (autogenerate) | Type | Feature | Description | Priority | Attachment | Assignee | Status | Assignee Comments | Notes
BUG - 0001 | Bug | Pricing | Packages color didn't changed after making changes in the color and theme settings. |  | https://prnt.sc/tsu98CLU3VRI |  | Complete
| Bug |  | Menu background color didn't changed in mobile version after making changes in the color and theme settings |  | https://prnt.sc/_IKVa3Y7uQST